## Slide 1
AfWA STC REPORT
SPECIALIZED TECHNICAL COMMITTEE 2
NRW and Water Quality

## Slide 2: COMMITTEE MEMBERSHIP
President: Aime Loukou
Vice President: Souleymane Sow
Rapporteur: Irene Nansubuga
Programes cordiantor: Alarfach AG Mohammed Ali
Members Participated : 34

## Slide 3: SUMMARY OF AGENDA ITEMS
Background
Progress Since Bamako Feb 2018
Future Plans

## Slide 4: Background
Background
Water Quality Task Force- AfriCap –Water Quality Mgt project
Improvement of Water quality management for selected countries
Burkina Faso (ONEA), Benin, Cote d’Ivoire, Guinea, Togo, Mali and Niger
Ghana (Ghana Water), Nigeria, Siera Leone and Liberia
Started 2015 to go up to 2019 (4 years)
Non Revenue Water Task Force – NRW Audit
Improvement of Capacity and performing the audit with regard to NRW reduction
21 Utilities from 17 countries (Table)
Started 2018 to go upto 2020
Follow up of 1st phase (15 auditors trained- but most no longer available, and 20 companies audited)

## Slide 5
Progress since Bamako Feb 2018
Water Quality Task Force- WQM project
  Exploratory Mission to 2 Labs in Nigeria – Anglophone lab
  Signing of Tripartite MOU with Utilities in Nigeria (improvement program)
  Bench marking visit by the Francophone lab completed
  Assistance Mission for Perfomance improvement Programme completed for the Francophone countries
Non Revenue Water Task Force- NRW Audit
  Theoretical training of 27 auditors from 14 countries
  Update of the Programme of the audit

## Slide 6: Future Plans - WQM project
Milestone | Activities | By when | By Who
Building capacity of Mentee Utilities | Benchmark visit of Nigeria to Ghana | 31st Aug 2018 | Mentor (GWCL)
Symposium of Water quality | Define Selection criteria of members of the Scientific committee (SC) | Done Today | WQ Task force
 | Propose members of the Scientific committee | Done Today | WQ Task force
 | Confirm and commission Scientific committee | 1st Aug 2018 | AFWA
 | Local organizing committee in place | 15th Aug 2018 | AFWA/Cam Water

## Slide 7: Future Plans Africap……2
Milestone | Activities | By when | By Who
Symposium of Water quality | Review and refine TOR | 31st Aug 2018 | SC
 | Call for Papers | 7rd Sep 2018 | SC
 | Receive Papers | 7thst Nov 2018 | SC
 | Complete Review and Selection of Papers | 21st Nov 2018 | SC
 | Communication to presenters | 30th Nov 2018 | SC
 | Symposium | 14th Dec 2018 | AFWA & LOC
 |  | 3 days before STC (Feb 2019) | AFWA & LOC

## Slide 8: Future Plans –NRW Audit

## Slide 9: Future Plans – NRW Audit……2
Milestone | Activities | By when | By Who
Auditing of Companies | Prepare concept Note for funding | Nov 2018 | TF
 | Preparation and submission of audit reports | Month after audits | TF
 | Bankable PIP and Strategic plans | Month after Audits | Audited Utilities
 | Donor funded Workshop | July 2019 | Audited Utilities & AFWA

## Slide 10
Thank You
Merci